## Cover sheet
Customer rollout template
|  |  |  | Version | 3.0
Customer name
PURPOSE
The purpose of this template is to provide a description of needed steps and a checklist for a successful Miradore implementation for an MSP's end customer.
The filled template can also be maintained as a log of the decisions made and tasks carried out (etc.) during the rollout.
STRUCTURE
Template structure is based on the typical Miradore rollout phases and steps, as depicted below.
Completion status of the checklist items is tracked in the subsequent table.
Phase | Description |  |  |  |  | ü | û
1. Initiation | Make decisions that set the frame for the rollout. Involve customer in this phase, if needed. |  |  |  |  | 0 | 18
2. Preparations | Obtain basic information, make operational decisions, ensure delivery capacity. |  |  |  |  | 0 | 20
3. Installations | Verify the delivery infrastructure, install Miradore system components, and test their functionality. |  |  |  |  | 0 | 21
4. Implementation | Implement Miradore modules as decided. |  |  |  |  | 0 | 30
5. Closing | Close the rollout project in a controlled way. |  |  |  |  | 0 | 4
USAGE
Blue cells denote static information. |  |  |  |  | White cells denote cells to which information should be entered.
White cells with selection list are used for indicating whether the item at issue has been addressed or not. |  | => | Done
No

## 1. Initiation
PHASE 1: INITIATION
1.1 | SCOPING DECISIONS
0 | Platforms | Windows | 1 |  |  | Done
|  | macOS | 0 |  |  | No
|  | Linux | 0
0 | Mobile platforms | Windows Phone | 0 |  |  | Done
|  | iOS | 0 |  |  | No
|  | Android | 0
0 | Miradore modules / features | Hardware Asset management | 1 | Mandatory module |  | Done
|  | Software Asset Management | 0 |  |  | No
|  | OS and Software Deployment Operating System and Software Deployment Operating System and Software Deployment | 0
|  | Endpoint Backup | 0
|  | Patch Management | 0
|  | Remote Assistance and Control | 0
0 | Device roles | Replace the text in this cell. List the device roles in scope. For example office workstations, special workstations. |  |  |  | Done
No
0 | Organizational coverage | Replace the text in this cell. Describe the organizational coverage of the rollout, for instance certain departments of the company, or certain subsidiary. |  |  |  | Done
No
0 | Geographical coverage | Replace the text in this cell. Describe the geographical coverage of the rollout, for instance certain country. |  |  |  | Done
No
0 | Integrations | Replace the text in this cell. To which systems are needed? What kind of integration? Example: 1. Service Desk, User and device data from Miradore to Service Desk system, one-way integration 2. Finance, asset purchase information from Miradore to Finance system, one-way |  |  |  | Done
No
0 | Data import | Replace the text in this cell. Describe what data will be imported from existing system(s) to Miradore. For example active devices and removed devices. |  |  |  | Done
No
1.2 | SERVICE ARCHITECTURE DECISIONS
0 | Miradore service delivery model | Replace the text in this cell. Describe the delivery model what comes to Miradore server locations, cloud vs. own premises considerations, make or buy considerations etc. |  |  |  | Done
No
1.3 | ROLLOUT DECISIONS
0 | Objectives | Replace the text in this cell. A free form description of the key objectives. |  |  |  | Done
No
0 | Definition of done | Replace the text in this cell. What activities and tasks have to be done when the rollout can be considered as finished. To be signed off in project closing phase. |  |  |  | Done
No
0 | Key roles: MSP | Service owner / Product manager |  | N.N. |  | Done
|  | Project manager |  | N.N. |  | No
|  | Architect |  | N.N.
|  | Trainer |  | N.N.
|  | Specialist, current situation analysis |  | N.N.
|  | Technical specialist(s) |  | N.N.
0 | Key roles: Customer | Service owner/Service delivery manager |  | N.N. |  | Done
|  | Technical specialist(s) |  | N.N. |  | No
0 | Schedule | Initiation |  | Start | Finish | Done
No
0 |  | Preparations |  | Start | Finish | Done
No
0 |  | Installations |  | Start | Finish | Done
No
0 |  | Service implementation |  | Start | Finish | Done
No
0 |  | Closing |  | Start | Finish | Done
No
Note on F59: Simo Kari: • Owner of the project • Assigns MSP project team
Note on F60: Simo Kari: • Drives the customer rollout • Coordinates daily activities
Note on F61: Simo Kari: • Provides comprehensive understanding on Miradore solution and different implementation scenarios • Participates actively in project activities
Note on F62: Simo Kari: • Provides Miradore training for the MSP or customer key resources (need depends on the delivery model)
Note on F63: Simo Kari: • Gathers all required current situation information from the customer environment
Note on F64: Simo Kari: • Provides expertise in one or more technical domains

## 2. Preparations
PHASE 2: PREPARATIONS
2.1 | BASIC INFORMATION
0 | Number of locations |  | Number of devices | Number of users | Done
No
0 | Miradore modules / features | Replace the text in this cell. Based in scope decided in the initiation phase. Describe any possible additional details that need to be taken into consideration during the prerequisites phase. |  |  | Done
No
0 | Delivery model | Replace the text in this cell. Based in delivery model decided in the initiation phase. Describe any possible additional details that need to be taken into consideration during the prerequisites phase. |  |  | Done
No
0 | What 3rd party products are in use (as relevant to scope)? | Replace the text in this cell. For example Active Directory, Antivirus, WSUS etc. |  |  | Done
No
2.2 | OPERATIVE DECISIONS
0 | Asset management: Client deployment method to be used | Replace the text in this cell. Using Miradore client deployer, 3rd party deployment tools, GPOs etc. |  |  | Done
No
0 | Configuration management: Installation points | Replace the text in this cell. Based on locations (and number of devices in locations) and network topology, plan the placement of installation points. Decide the place for media master. |  |  | Done
No
0 | Configuration management: Operating systems | Replace the text in this cell. Based on the platforms in scope, elaborate what versions etc. will be installed. For example Windows 7, Windows 10, Windows Server 2016 etc. |  |  | Done
No
0 | Configuration management: Software | Replace the text in this cell. Decide the software in the scope of the rollout project. |  |  | Done
No
0 | Configuration management: Naming standards | Replace the text in this cell. Review and decide naming standards. |  |  | Done
No
0 | User data backup: Scope of backup | Replace the text in this cell. Decide what user data will be backed up. |  |  | Done
No
0 | User data backup: Delivery model | Replace the text in this cell. Decide the delivery model (cloud, customer premises etc.) for user data backup. |  |  | Done
No
0 | Self-service portal: Look and feel customization | Replace the text in this cell. Is there a need for self-service portal look and feel customization? For example logos. |  |  | Done
No
0 | Self service portal: Profile customization | Replace the text in this cell. Is there a need for self-service portal profile customization? For example what is shown in portal and for which type of devices. |  |  | Done
No
0 | Connectors | Replace the text in this cell. Decide which connectors are needed to 3rd party systems. |  |  | Done
No
0 | Miradore roles | Replace the text in this cell. Decide Miradore roles to be used. For example who needs what kind of access, do customer personnel need permissions? If clearly standardized roles exist, list possible exceptions here. Mandatory role in this phase: system administrators. |  |  | Done
No
2.3 | DELIVERY CAPACITY
0 | Miradore instance server | Verify that server capacity exists, place the order if not. |  |  | Done
No
0 | Database server | Verify that server capacity exists, place the order if not. |  |  | Done
No
0 | Other servers | Verify that server capacity exists for other in-scope services, place the order if not. For example Mail server. |  |  | Done
No
0 | Connectivity | Verify if data communications changes are needed, place the order if yes. Order needed firewall openings. |  |  | Done
No
0 | Connectors | Verify what are the servers to which connector(s) will be installed. For example installation to existing server in customer network. |  |  | Done
No

## 3. Installations
PHASE 3: INSTALLATIONS
3.1 | INFRASTRUCTURE VERIFICATIONS
0 | Server capacity | Miradore instance server: [Name, IP address, access rights, readiness] | Done
No
0 |  | Database server (name, IP address, access rights, readiness) | Done
No
0 |  | MSP console (name, IP address, access rights) | Done
No
0 |  | Remote control server (name, IP address, access rights) | Done
No
0 |  | Mail server for SMTP settings (name, SMTP port, sender address) | Done
No
0 |  | Patch management / master installation point (name, IP address, access rights) | Done
No
0 | Connectivity | MSP console <-> Miradore instance server | Done
No
0 |  | Miradore instance server <-> Database server | Done
No
0 |  | Managed clients -> Miradore instance server (https) | Done
No
0 |  | Miradore instance server -> Managed clients (wake-up) | Done
No
0 |  | SSL certificate | Done
No
3.2 | INSTALLATIONS
0 | Customer instance setup | Install Miradore Management Suite software. | Done
No
0 | Joining to MSP Console | Register the Miradore Management Suite instance to MSP Console. | Done
No
0 | User permissions | Implement Miradore user permissions and roles based on decisions done earlier. | Done
No
0 | Installation of connectors | Install the 3rd party connectors decided earlier. | Done
No
0 | Miradore client deployment method setup | Based on the method decided earlier, set up the capability to deploy Miradore clients. | Done
No
0 | Service-specific settings | Based on the decisions made earlier, enable features in Miradore system settings. | Done
No
0 | MSP-specific settings | Configure MSP-specific standard system settings. | Done
No
0 | Customer-specific settings | Configure customer-specific settings, such as locations, organizations, and subnets. | Done
No
3.3 | TESTING
0 | Connectors | Check that “successful status” received to Miradore event log. Check that data received to Miradore. | Done
No
0 | Client deployment | Check that deployment can be started successfully. | Done
No

## 4. Implementation
PHASE 4: IMPLEMENTATION
4.1 | HARDWARE ASSET MANAGEMENT
0 | Client deployment | Client deployment is started to selected target device group. | Done
No
0 | Physical attributes | Verify correctness of physical attributes (HW category, HW model). | Done
No
0 | Logical attributes | Verify correctness of logical attributes (location, organization, responsible person, device role, device usage). | Done
No
0 | Contractual attributes | Verify correctness of contractual attributes (SW, HW, or service contracts). | Done
No
0 | Asset lifecycle | Configure asset lifecycle status definitions. | Done
No
0 | Asset tags | Review asset tag name generation profile. | Done
No
0 | Asset information | Configure asset information update and confirmation process. | Done
No
0 | Asset labels | Configure asset label printing profiles. | Done
No
0 | Inventory intervals | Verify standard inventory intervals. | Done
No
0 | Custom inventory | Decide custom inventory configurations. | Done
No
4.2 | OPERATING SYSTEM AND SOFTWARE DEPLOYMENT
0 | Installation points | Configure installation point hierarchy (media master and replicas). | Done
No
0 | Initial installation | Configure initial installation settings (operating system, location and organization specific settings etc.) | Done
No
0 | Software packages | Configure software and configuration packages which are in the scope of the rollout project. | Done
No
4.3 | SOFTWARE ASSET MANAGEMENT
0 | Licensable software | Identify licensable software. | Done
No
0 | License pools | Create required license pools. | Done
No
0 | License allocation | Create license allocation rules. | Done
No
0 | Software usage metering | Set up software usage metering. | Done
No
4.4 | ENDPOINT BACKUP
0 | Miradore Backup installation | Install Miradore Backup server, if http(s) used. | Done
No
0 | Backup storage setup | Set up file system, USB disk, or NAS as the backup storage. | Done
No
0 | Backup jobs | Configure backup jobs. | Done
No
0 | Permissions | Set up permissions and user accounts. | Done
No
4.5 | PATCH MANAGEMENT
0 | Miradore Patch management installation | Install Miradore installation point and patch updater | Done
No
0 | Patch scoping | Enable patch management and configure patch scopes in system settings | Done
No
0 | Create asset groups | Create asset groups for patch management (e.g. pilot group) | Done
No
0 | Permissions | Set up permissions and user accounts. | Done
No
4.6 | REMOTE ASSISTANCE AND CONTROL
0 | Miradore Remote control installation | Install Miradore Remote control server | Done
No
0 | Install remote control admininstrator clients | Install remote control admininstrator clients | Done
No
0 | Configure remote control | Configure remote control settings in Miradore | Done
No
0 | Remote control clients | Install remote control clients | Done
No
0 | Permissions | Set up permissions and user accounts | Done
No

## 5. Closing
PHASE 5: CLOSING
5.1 | HANDOVER TO PRODUCTION
0 | Handover to server hosting | Ensure that installed customer environment is included in a backup scheme, being monitored, being patched etc. Ensure that service documentation is available for hosting. | Done
No
0 | Handover to service support | Ensure that service documentation is available for service support and that they have received needed training. | Done
No
5.2 | AFTERCARE ACTIVITIES
0 | Agree aftercare activities | Replace the text in this cell. Record the agreed aftercare activities, including responsibilities and schedules. | Done
No
5.3 | SIGN-OFF
0 | Sign-off from customer representative | Based on the "Definition of done" agreed in the Initiation phase, review the rollout outcome with customer representative. Obtain customer approval for rollout closing. | Done
No

## Sheet1 (hidden)
Pick | 0
0
1